## Features
Feature & Lego-block catalogue
Module | Feature / Lego-block | Description | Status | Priority | Milestone | Notes
Core engine | Namespaced counter-RNG | Philox/Threefry keyed on (subsystem, spin, draw) | Done | P0 | M1 | ADR-003 keystone
Core engine | Integer / u128 accounting | smallest-unit money; decimal only at boundary | Done | P0 | M1 | ADR-002
Core engine | Exact enumeration RTP | full reel-stop enumeration / convolution | Done | P0 | M1 | ADR-001 cert source of truth
Core engine | Line-eval Lego blocks | LTR / both-ways / ways-243, scatter & wild rules | Done | P0 | M1 | parity-critical semantics
Core engine | Deterministic Monte Carlo | Rayon; seed-replay identical to the unit | Done | P0 | M1 | validates harness
Core engine | Streaming integer stats | fixed histogram + per-line/symbol counters | Done | P0 | M1 | ADR-012
Core engine | Max-win cap inside math | min(win, cap) inside convolution & sim | Done | P0 | M1 | ADR-005
Core engine | Minimal numeric math sheet | CSV/JSON exact + MC output | Done | P1 | M1
Core engine | CLI | run exact + MC on a config | Done | P1 | M1
Solver | CMA-ES + penalty constraints | optimize against the exact engine | Planned | P0 | M2 | ADR-006
Solver | Common Random Numbers | variance reduction for MC parts | Planned | P0 | M2 | depends on ADR-003
Solver | Weights -> strip realize + re-verify | preserve positional/adjacency constraints | Planned | P1 | M2 | ADR-006
Solver | Anti-degeneracy constraints | gameplay-shape targets as hard constraints | Planned | P0 | M2 | no boring math
Solver | RTP-by-feature decomposition | contributions reconcile to the unit | Planned | P1 | M2 | anti-degeneracy signal
Solver | PyO3 bindings | Rust core in-process to Python | Planned | P1 | M2 | ADR-007
AI layer | LLM context translator | constrained decoding from fixed Lego library | Planned | P0 | M3 | ADR-008; never writes code
AI layer | Pydantic validation | models generated from schema | Planned | P0 | M3 | ADR-004
AI layer | FastAPI orchestration | translate / validate / simulate / tune | Planned | P1 | M3
Frontend | Schema-driven form | generated from schema; locks hard bounds | Planned | P0 | M3 | ADR-004
Frontend | Monaco JSON editor | raw config view / tweak | Planned | P2 | M3
Frontend | Persistence (Postgres/SQLite) | store configs + results | Planned | P1 | M3 | connector at M3
Frontend | Playwright E2E | end-to-end tests | Planned | P1 | M3 | blueprint-mandated
Compliance | Advanced mechanics | cascades / expanding wilds / multipliers | Planned | P0 | M4 | MC + Markov
Compliance | GLI/BMM exporter | PDF/Excel certification math sheet | Planned | P0 | M4
Compliance | Confidence intervals | on every Monte Carlo metric | Planned | P1 | M4 | ADR-009

## Metrics
Metrics — definitions, targets, and how we test them
Metric | Definition | Target | Current | Unit | Source module | Test method
RTP (exact) | total_won / total_bet, computed exactly | per design (e.g. 96.00) | 95.30 | % | core-math | enumeration vs certified sheet
RTP (Monte Carlo) | MC estimate of RTP, with CI | CI contains exact value | 95.34 +/- 0.11 | % | core-math | 10M+ spins
Volatility | std dev of per-spin return | per design (e.g. med-high) | 2.47 | sigma | core-math | integer sum-of-squares
Hit frequency | share of spins with any win | per design | 51.33 | % | core-math | per-spin counter
Bonus frequency | share of spins triggering bonus | per design (e.g. 1/180) |  | 1/x | core-math | counter
Max-win probability | P(total win reaches the cap) | small |  | prob | core-math | counter
% RTP at cap | RTP delivered at the max-win cap | low (guard metric) |  | % | core-math | ADR-005 guard
Spin throughput | Monte Carlo spins per second | 10M < 2s (>=5M/s) | ~19M/s (10M in 0.55s) | spins/s | core-math | benchmark
Determinism | seed-replay reproducibility | 50/50 identical to the unit | PASS (thread-independent) | pass/fail | core-math | seed replay across threads
Exact-vs-MC delta | ¦exact - MC¦ relative to CI | within CI | within 95% CI | % | core-math | parity harness
Parity deviation (exact) | exact RTP vs certified sheet | < 0.001 | pending external game | % | core-math | Math Parity Test
Schema validation pass-rate | stylized prompts -> schema-valid JSON | 100 |  | % | ai-layer | fuzz test (1000 prompts)
RTP reconciliation | sum of feature contributions = total | exact to the unit |  | units | core-math | decomposition check

## Milestones
Milestones & gates
Milestone | Version | Deliverable | Gate / acceptance | Status
Foundation | v0.1.0 | repo, branching, ADRs, draft schema, tooling | clean documented checkpoint | Done
M1 | v0.2.0 | Core Math Engine (5x3 lines) | Parity Test passes; seed-replay identical; 10M < 2s | In progress
M2 | v0.3.0 | Auto-Tuner / Solver | broken 140% RTP config -> fixed playable 96% | Planned
M3 | v0.4.0 | AI translator + FastAPI + frontend | prompt -> JSON -> simulate -> tune in browser | Planned
M4 | v1.0.0 | Advanced mechanics + GLI/BMM exporter | exported sheet matches a certified live game | Planned

## Versions
Release / rollback log
Version | Type | Date | Summary | Rollback notes
v0.1.0 | stable | 2026-06-16 | Foundation: repo, stable/beta branching, ADRs, draft schema, workbook, plugins | baseline checkpoint; git checkout v0.1.0
v0.2.0-beta.1 | beta | 2026-06-16 | M1 core-math engine: namespaced RNG, integer accounting, exact+MC, CLI; 6 tests green (~19M spins/s) | last stable = v0.1.0; git checkout v0.1.0